## S2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 02.Finance Management | 2.01 | Booking Fees Calculation | Implementation of Fees calculation algorithm and add federal,State and Service tax to the actual price | 2024-12-03 | 03-20-2024 | 100% | Harish
2 | 02.Finance Management | 2.02 | Financial Reporting | Establishing secure payment using third party API | 2024-12-03 | 03-20-2024 | 100% | Dheeraj
3 | 02.Finance Management | 2.02 | Financial Reporting | Implementation of Credit/Debit Card/Apple Pay | 2024-12-03 | 03-20-2024 | 100% | Dheeraj
4 | 02.Finance Management | 2.02 | Financial Reporting | Implemantation of Payment page | 2024-12-03 | 03-20-2024 | 100% | Maniraj Mukka
5 | 02.Finance Management | 2.02 | Financial Reporting | Test the integration of the third-party payment API and functionality of credit/debit card and Apple Pay options | 2024-12-03 | 03-20-2024 | 50% | pakkela pavan
6 | 04.Customer Support | 4.01 | Ticket Handling inquiry | Getting User data for user identity | 2024-12-03 | 2024-04-04 | 100% | Monil Mody
7 | 04.Customer Support | 4.01 | Ticket Handling inquiry | Retrieving FAQ information so that user can access it | 2024-12-03 | 2024-04-04 | 100% | Smith Dsouza
8 | 04.Customer Support | 4.01 | Ticket Handling inquiry | Implement an advanced field validation mechanism for the ticket inquiry submission form to ensure all customer-provided information is complete and valid before submission. | 2024-12-03 | 2024-04-04 | 100% | Dheeraj
9 | 04.Customer Support | 4.01 | Ticket Handling inquiry | Test the retrieval process of user data for identity verification,functionality of retrieving FAQ information,advanced field validation mechanism on the ticket inquiry form and security features of the platform’s communication channels | 2024-12-03 | 2024-04-04 | 100% | Pakkela Pavan
10 | 04.Customer Support | 4.02 | Issue resolution and refunds | Fetch User transaction detail Implement refund process system | 2024-12-03 | 2024-04-04 | 100% | Harish
11 | 04.Customer Support | 4.02 | Issue resolution and refunds | Develop an automated system to handle customer issues and refund requests based on product type. | 2024-12-03 | 2024-04-04 | 100% | Monil Mody
12 | 04.Customer Support | 4.02 | Issue resolution and refunds | Access to user account and handle refund dead locks when connection is weak | 2024-12-03 | 2024-04-04 | 100% | Mehul
13 | 04.Customer Support | 4.02 | Issue resolution and refunds | Test the functionality of fetching user transaction details,Ensure Efficacy of Refund Process System,Test the automated system for handling issues and refunds by product type and Confirm Refund Handling Under Weak Connection Conditions | 2024-12-03 | 2024-04-04 | 100% | Maniraj Mukka
14 | 04.Customer Support | 4.03 | User Communication | Develop an automated response system for swiftly addressing issues raised by external users, with tailored communications based on their specific entitlements and a feedback mechanism to evaluate resolution effectiveness. | 2024-12-03 | 2024-04-04 | 100% | Mehul
15 | 04.Customer Support | 4.03 | User Communication | Design and deploy a targeted messaging platform within SwiftRails that recognizes and adapts to the specific access rights and roles of external users, providing tailored updates, notifications, and support communications to enhance engagement and satisfaction | 2024-12-03 | 2024-04-04 | 100% | Mehul
16 | 04.Customer Support | 4.03 | User Communication | Test the automated response system and adaptability of the messaging platform | 2024-12-03 | 2024-04-04 | 100% | Maniraj Mukka
17 | 05.Advertising Management | 5.01 | Ad inventory management | Implement role-based access control (RBAC) for third-party advertising partners to manage the ad inventory | 2024-12-03 | 2024-04-04 | 100% | Koushik
18 | 05.Advertising Management | 5.01 | Ad inventory management | Develop a dynamic categorization system for ad products, allowing for the automatic classification of ads based on content, target audience, and other metadata. | 2024-12-03 | 2024-04-04 | 100% | Koushik
19 | 05.Advertising Management | 5.01 | Ad inventory management | Design and implement a comprehensive field validation process for ad submission forms | 2024-12-03 | 2024-04-04 | 100% | Koushik
20 | 05.Advertising Management | 5.01 | Ad inventory management | Establish real-time connectivity between the SwiftRails ad inventory management system and external ad exchanges or platforms. | 2024-12-03 | 2024-04-04 | 100% | Koushik
21 | 05.Advertising Management | 5.01 | Ad inventory management | Test RBAC System for Third-Party Advertising Partners,Validate the Dynamic Ad Categorization System,Ensure Accuracy of Ad Submission Form Field Validation and Test Real-Time Connectivity with External Platforms | 2024-12-03 | 2024-04-04 | 100% | Pakkela pavan
[7 empty] | Owner | Shashank Mishra
[7 empty] | Contributor | Monil Mody
[7 empty] | Peer Reviewer | PriyaBhavna

## S3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 03.Product Management | 3.01 | Ticket Inventory Management | Implement a ticket activation option in the navbar, an activation confirmation interface, and an automated email notification system. | 2024-09-04 | 2024-07-05 | 100% | Dipesh Bharambe
2 | 03.Product Management | 3.01 | Ticket Inventory Management | Develop field validation checks to confirm ticket selection and activation, with clear error messages and confirmation prompts, ensuring a smooth and error-free activation process. | 2024-09-04 | 2024-07-05 | 100% | Dipesh Bharambe
3 | 03.Product Management | 3.01 | Ticket Inventory Management | Implement reliable backend connectivity protocols and fallback mechanisms to maintain a consistent connection during the ticket activation process, with real-time feedback to the user. | 2024-09-04 | 2024-07-05 | 100% | Dipesh Bharambe
4 | 03.Product Management | 3.01 | Ticket Inventory Management | Validate that each step in the ticket activation process has appropriate field checks and that incorrect inputs are handled with clear, informative error messages. Confirm that upon successful activation, the system presents a clear confirmation message and that the UI reflects the new state of the ticket (activated). | 2024-09-04 | 2024-07-05 | 100% | Dipesh Bharambe
5 | 03.Product Management | 3.02 | Event Scheduling and Planning | Create an event scheduling feature within the system that provides real-time updates on train schedules, calculates travel times, and integrates a rail map view for enhanced journey planning. | 2024-09-04 | 2024-07-05 | 100% | Monil Mody
6 | 03.Product Management | 3.02 | Event Scheduling and Planning | Implement field validation for train schedule queries to verify station names and destinations, and ensure the rail map reflects accurate, up-to-date train route data. | 2024-09-04 | 2024-07-05 | 100% | Monil Mody
7 | 03.Product Management | 3.02 | Event Scheduling and Planning | Develop robust connectivity and data retrieval systems to maintain uninterrupted access to real-time train schedules and rail map information, even in low-bandwidth scenarios. | 2024-09-04 | 2024-07-05 | 100% | Monil Mody
8 | 03.Product Management | 3.02 | Event Scheduling and Planning | Design and implement a data flow architecture that ensures real-time updates from train schedule databases to the user interface, with efficient processing for displaying accurate train arrivals, travel times, and rail map data. | 2024-09-04 | 2024-07-05 | 100% | Monil Mody
9 | 03.Product Management | 3.02 | Event Scheduling and Planning | Confirm real-time updates, journey planning, and scheduling functionality. Evaluate user interface ease and response under load.Check input validation for schedule queries and provide clear error messages.Ensure accurate and current train route data in the rail map.Test data retrieval under varied network conditions, including low bandwidth. Assess fallback mechanisms for network disruptions. Validate seamless real-time updates from databases to user interface. Ensure efficient processing for accurate train information display. | 2024-09-04 | 2024-07-05 | 100% | Monil Mody
8 | 03.Product Management | 3.03 | Promotions and Discounts | Implement a promotions and rewards system that tracks user spending on tickets, awards points accordingly, displays targeted ads, and allows users to redeem points for merchandise or tickets. This includes creating an interface for tracking and redeeming points, as well as integrating with the advertising system. | 2024-09-04 | 2024-07-05 | 100% | Smith
9 | 03.Product Management | 3.03 | Promotions and Discounts | Develop a tiered promotional points system that allocates rewards according to the product type of the ticket purchased, and integrates with an ad server to display personalized ads, ensuring customers can track and use their points for merchandise or ticket redemption within the platform. | 2024-09-04 | 2024-07-05 | 100% | Koushik
10 | 03.Product Management | 3.03 | Promotions and Discounts | Create a resilient connectivity framework for the loyalty points system that ensures reliable access to promotional points balance, ads, and the redemption process, with offline support for basic functionality where possible. | 2024-09-04 | 2024-07-05 | 100% | Koushik
11 | 03.Product Management | 3.03 | Promotions and Discounts | Design and implement a data flow strategy that accurately tracks customer spending on different ticket types, updates promotional points in real-time, and serves targeted ads based on the product type, ensuring smooth data synchronization across the platform. | 2024-09-04 | 2024-07-05 | 100% | Koushik
12 | Product Management | 3.03 | Promotions and Discounts | Verify that the system accurately tracks spending and awards points based on user ticket purchases. Test the redemption process for external entitlements like merchandise or tickets, ensuring that the points are deducted correctly and the entitlements are granted. Check that the points awarded are correctly tiered based on the product type of the ticket.Test the system’s resilience by simulating network outages to see if it can still perform basic functions offline. Confirm that once connectivity is re-established, the system syncs and updates all user activities performed offline. Validate real-time tracking and updating of promotional points upon customer actions. Ensure that the data flow is seamless and consistent across all parts of the system, with no discrepancies in points balances or user data. | 2024-09-04 | 2024-07-05 | 100% | Koushik
13 | 05.Advertisement Management | 5.02 | Campaign Creation and Monitoring | Develop a system for campaign creation that allows for the setup and display of promotional ads, along with monitoring tools to track campaign performance and customer engagement metrics for external entitlements. | 2024-09-04 | 2024-07-05 | 100% | Monil Mody
14 | 05.Advertisement Management | 5.02 | Campaign Creation and Monitoring | Implement a campaign management module that allows creation of product-type-specific ad campaigns, with tracking capabilities to monitor customer responses and adjust strategy for each product type accordingly. | 2024-09-04 | 2024-07-05 | 100% | Monil Mody
15 | 05.Advertisement Management | 5.02 | Campaign Creation and Monitoring | Establish a dependable connectivity infrastructure for delivering promotional ad campaigns, with mechanisms to cache ads locally for viewing during intermittent connectivity issues, ensuring constant customer engagement with our product types. | 2024-09-04 | 2024-07-05 | 100% | Monil Mody
16 | 05.Advertisement Management | 5.02 | Campaign Creation and Monitoring | Create ad campaigns for different product types and monitor their setup accuracy. Use the monitoring tools to track engagement and performance metrics, focusing on how they relate to external entitlements.Simulate campaign setups for multiple product types and assess ad targeting precision. Track engagement and performance metrics using the system’s tools, ensuring they reflect user interactions with external entitlements. Alter ad campaign strategies based on gathered data and observe system responsiveness. Test connectivity resilience by disrupting network access and evaluating offline ad caching and subsequent data sync. | 2024-09-04 | 2024-07-05 | 100% | Monil Mody
17 | 05.Advertisement Management | 5.03 | User Targeting Personalize | Design and implement a user targeting system that analyzes customer behavior and preferences to serve personalized ad campaigns, ensuring the content is relevant to each individual's interests and past interactions with our product types. | 2024-09-04 | 2024-07-05 | 100% | Supraja
18 | 05.Advertisement Management | 5.03 | User Targeting Personalize | Create a feature within the advertising system that segments users by product interest, dynamically aligns ad content with their preferences, and monitors engagement to refine ad targeting for each product type. | 2024-09-04 | 2024-07-05 | 100% | Supraja
19 | 05.Advertisement Management | 5.03 | User Targeting Personalize | Develop a resilient ad delivery network that maintains persistent user targeting and personalization for various product types, including mechanisms for gracefully handling fluctuations in user connectivity. | 2024-09-04 | 2024-07-05 | 100% | Supraja
20 | 05.Advertisement Management | 5.03 | User Targeting Personalize | Interact with products and check for ad relevance. Monitor ad adjustments following user engagement changes. Test ad delivery during network instability. | 2024-09-04 | 2024-07-05 | 100% | Supraja
[7 empty] | Owner | Shashank Mishra
[7 empty] | Contributor | Monil Mody
[7 empty] | Peer Reviwer | Monil Mody