## User Stories
USER STORIES - SWIFTRAILS | [5 empty] | Owner - Monil Samir Mody
Contributor - Smith Dsouza
Peer Reviewer - Smith Dsouza
Module | Title | As a/an | I want to… So that I can… | Sprint | Story Points | Story Constraints | Story Exceptions
01. Account management | 01.01 User registration | Client Manager, Product Manager | Implement UI for create account page and login page -> user-email, password, last-name, first-name, phone-number(optional) | S1 | 5 | Validate input fields (e.g., email, password) to meet specified criteria for format and strength. Implement robust exception handling to handle errors gracefully during the registration process. | If a user attempts to register with an email address that already exists in the system, an error message should be displayed indicating that the email is already registered. Log this exception to track the occurrence and potential trends for further analysis. FV-field validation. Implement mechanisms to handle requests from external systems or APIs for user data access securely. ETout - external entitlements
| 01.02 Login and Authentication | Client Manager, Product Manager | Validate, authenticate and authorize the user in database, if exist -> user already exist; if doesn’t exist -> create a new account; save the user data in database with update and delete calls -> attributes to consume and save it in databse -> user-email, password, last-name, first-name, phone-number(optional) | S1 | 5 | Validate user credentials against the database during login. Authenticate users by verifying their identity with the provided credentials. Authorize access based on user roles or permissions.OTP functionality for validating the users authenticity. | Handle unauthorized access attempts by redirecting users to the login page or displaying error messages.ETin- internal entitlements. Log exceptions and handle them during registration for debugging purposes. ExHL - Exception handling and logging. Handle database connection failures gracefully and retry mechanisms for network issues.CN - connectivity
| 01.03 Profile management | Client Manager, Product Manager | Create database and queries to consume the user data in json format, and Implementation of profile page (UI) -> POPULATE these fields -> user-email, password, last-name, first-name, phone-number, Redirect to the home page, Knowing about the company, Viewing the pre-booked tickets Servicers they provide and Contact details so that it is very easy for a new or an existing user to get started. | S1 | 7 | Only authenticated users with appropriate permissions can access and manage their profiles. Etin - internal entitlements | The format of the data coming for the API should be in json format Etout - external entitlements.Can't see ticket section if you're not logged in FV- Field validation.
02. Finance Management | 02.01 Booking fees calculation | Accountant, Product Manager | User should be able to book their tickets by coming to the scheduled train timings and also need to evaluate ticket fees calculation | S1 | 3 | Validate user input for booking tickets, ensuring it meets specified criteria. | Optimize fee calculation algorithms to handle high volumes of ticket bookings without performance degradation PF - performance
| 02.02 Financial reporting | Accountant, Product Manager | To pay money through a safe payment method using credit cards, debit card, and apple pay to get the ticket using the third party API | S2 | 3 | Only one payment method at a time and third-party API restrictions. Implement robust exception handling during payment processing and reporting. | Implement secure payment methods and integrate with third-party APIs for safe and reliable financial transactions. Etout - external entitlements
| 02.03 Upload Products | Product Manager | Redirect to a page which will further give me options to book a ticket | S1 | 5 | Ensure seamless integration with the upload product page to provide options for booking tickets. | Handle data flow from the upload product page to the ticket booking page securely and efficiently. Siin - system interface - inbound
03. Product Management | 03.01Ticket Inventory Management | Product Manager | View and activate the tickets which the user already booked for the ride. Nav bar -> Tickets -> Choose the ticket you want to activate -> Once you clikc on the ticket it will show the options for activating the ticket -> once you press that, the ticket would be activated and ready to scan. The user will also recieve an email notification with their ticket. | S3 | 5 | You can't view or activate the ticket till you buy it. You can activate one ticket only once. Only authenticated users with appropriate permissions can view and activate tickets. Ensure accurate data flow of ticket inventory information from the database to the UI. | Handle data retrieval and display errors gracefully to provide users with up-to-date ticket information. Dfin - data flow in.
| 03.02 Event Scheduling and Planning | Product Manager | To check which train will arrive at what time at what station and how much time will it take for the train to reach the desired destination & View Railmap. | S3 | 4 | Integrate with external systems or APIs to retrieve train schedules and event planning information. | Handle data retrieval from external sources securely and efficiently to display train schedules and event plans accurately. Siout - system interface -Outbound
| 03.03 Promotions and discounts | Accountant, Product Manager | User will be shown ads and promotion points for the each dollar they spend on the ticket and comsume them on merchendize or use points get a free ticket. | S3 | 3 | Validate user input for promotional codes and discounts during ticket booking. | Provide feedback for invalid or expired promotional codes and discounts entered by users. FV - Field validation
04. Customer Support | 04.01 Ticket handling inquiry | Customer Support Specialist, Product Manager | We can create an FAQ page where user can go and see if they can find the solution for the problem they are facing. | S2 | 2 | Retrieve FAQ information from the database to display on the FAQ page. | Ensure accurate data retrieval and display of FAQ information to assist users in finding solutions to their inquiries. Siout - system interface - outbound
| 04.02 Issue resolution and refunds | Customer Support Specialist, Product Manager | If a user faces issues while booking tickets, they can reach out to us to by chat or call for refund. | S2 | 4 |  | Log errors encountered during issue resolution and refund requests for analysis and troubleshooting, and provide users with timely refunds. ExHL - Exception handling and logging
| 04.03 User communication | Customer Support Specialist, Product Manager | User can chat or call customer support | S2 | 4 | Handle user communication requests via chat or call and route them to the appropriate customer support specialist. | Ensure seamless integration of chat and call functionality to facilitate effective communication between users and customer support. Siin - system interface - inbound
05. Advertisement Management | 05.01 Ad inventory management | Product Manager, Advertising Manager | create Ads, manage ads, categories of ads so we can create revenue out of ads. | S2 | 2 | Implement caching mechanisms to manage ad inventory efficiently and improve system performance. | Ensure accurate and up-to-date ad inventory management to optimize revenue generation from ads. CA - cache
| 05.02 Campaign creation and monitoring | Product Manager, Advertising Manager | Create campaigns to attract customers by showing promotional ads | S3 | 2
| 05.03 User targeting personalize | Product Manager, Advertising Manager | Targeting the right audience and giving them ads according to their interests | S3 | 2 | Retrieve user targeting information from the database to personalize ads based on user interests. | Ensure accurate data retrieval and display of personalized ads to target the right audience effectively. Siout - system interface - outbound