## roadmap
SWIFTRAILS ROADMAP |  |  | TICKET RESERVATION PORTAL
|  |  | SPRINT1 | SPRINT2 | SPRINT3
APPLICATION MODULES | FEATURE BACKLOG | STORY POINTS | SPRINT1(02/21/24 -- 03/12/24) | SPRINT2(03/13/24 -- 04/09/24) | SPRINT3(04/10/24 -- 05/07/24)
01. Account Management | 01.01 User registration | 5 | x
| 01.02 Login and Authentication | 4 | x
| 01.03 Profile management | 3 | x
02. Finance Management | 02.01 Booking fees calculation | 5 | x
| 02.02 Financial reporting | 4 |  | x
| 02.03 Upload Products | 3 |  | x
03. Product Management | 03.01 Ticket Inventory Management | 5 |  |  | x
| 03.02 Event Scheduling and Planning | 4 |  |  | x
| 03.03 Promotions and discounts | 4 |  |  | x
04. Customer Support | 04.01 Ticket handling inquiry | 5 |  | x
| 4.02 Issue resolution and refunds | 4 |  | x
| 04.03 User communication | 3 |  | x
05. Advertisement Management | 05.01 Ad inventory management | 4 |  | x
| 05.02 Campaign creation and monitoring | 5 |  |  | x
| 05.03 User targeting personalize | 2 |  |  | x
|  | VELOCITY | 20 | 20 | 20